## hieuth8653
| Actual working hour table |  |  |  | Plan effort | 0 | Actual effort | 0 | date time
| Division |  |  |  | Name |  | Email |  | 2017-01-01
| Working day | 2016-12-01 | 20 | days | Report from |  | Report to
[18 empty] | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
No | project | Ticket ID | Parent ID | Ticket subject | Description (VN/JP) | Ticket Type | Source ID | Version/Release | Activity | Progress (%) | Status | LOC | Test Case | Start date (mm/dd/YYYY) | End date (mm/dd/YYYY) | Estimate (H) | Actual (H) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Measurement tool | 4817 |  | [Document] Investigate GA report |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-03 | 2015-12-22 | 8.5 | 0 | 1: 8.5
| Measurement tool | 4818 |  | 「TEST」テストケースを準備してください |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-04 | 2015-12-04 | 8 | 0 | 1: 30.5
| Measurement tool | 4819 |  | [Testing] Execute test before/after release |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-05 | 2016-12-23 | 93.5 | 0 | 1: 93.5

## thanhnb6719
| Actual working hour table |  |  |  | Plan effort | 0 | Actual effort | 0 | date time
| Division |  |  |  | Name |  | Email |  | 2016-12-12
| Working day | 2016-12-01 | 20 | days | Report from |  | Report to
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
tracker
No | Project | tICket ID | Parent ID | Ticket Subject | Description (VN/JP) | Ticket Type | Source ID | Version/Release | Activity | Progress (%) | Status | LOC | Test Case | Start date (mm/dd/yyyy) | End date (mm/dd/yyyy) | Estimate (H) | Actual (H) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Measurement tool | 4820 |  | [Management] Management_QA |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-07 | 2016-12-12 | 8 | 0 | 1: 8
| Measurement tool | 4821 |  | aaaaa |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-07 | 2016-12-12 | 6 | 0 | 1: 6
| Measurement tool | 4822 |  | [Management] Management_QA |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-06 | 2016-12-06 | 4.5 | 0 | 1: 4.5
| Measurement tool | 4823 |  | [Management] Management_QA |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-02 | 2016-12-02 | 29.5 | 0 | 1: 29.5
| Measurement tool | 4824 |  | [Management] Management_QA |  | Test | Cowell Redmine |  | Test |  | In Progress | 0 |  | 2016-12-02 | 2016-12-26 | 90 | 0 | 1: 80
| Measurement tool | 4825 |  | 【Monthy】Import mother server file |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-06 | 2016-12-06 | 16 | 0 | 1: 16
| Measurement tool | 4826 |  | [Test] Executing test data |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-01 | 2015-12-31 | 34 | 0 | 1: 17

## huent6651
| Actual working hour table |  |  |  | Plan effort | 0 | Actual effort | 0
| Division |  |  |  | Name |  | Email
| Working day | 2016-12-01 | 20 | days | Report from |  | Report to
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
tracker
No | Project | Ticket ID | Parent ID | Ticket SuBject | DESCRIPTION (VN/JP) | Ticket Type | Source ID | Version/Release | Activity | Progress (%) | Status | LOC | Test Case | Start date (mm/dd/yyyy) | End date (mm/dd/yyyy) | Estimate (H) | Actual (H) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Measurement tool | 4827 |  | Research RankingBuilderV3 - Flow code and implement |  | Code | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-06 | 2016-12-06 | 24 | 0 | 1: 24
| Measurement tool | 4828 |  | [Release] Remove condition NOT NULL of T_JOIN_DATA |  | Code | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-03 | 2015-12-31 | 32 | 0 | 1: 64
| Measurement tool | 4829 |  | 【Research】Gwin-BBS |  | Code | Cowell Redmine |  | Test |  | In Progress | 0 |  | 2016-12-06 | 2016-12-06 | 55 | 0 | 1: 55
| Measurement tool | 4830 |  | 【Research】Node JS + AWS |  | Code | Cowell Redmine |  | Test |  | Resolved | 0 |  | 2016-12-02 | 2016-12-02 | 45 | 0 | 1: 47