## ninhcth6379
| Actual working hour table |  |  |  | Plan effort | 0 | Actual effort | 0 | date time
| Division |  |  |  | Name |  | Email |  | 2016-12-12
| Working day | 2016-12-01 | 20 | days | Report from |  | Report to
[18 empty] | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
No | Project | Ticket ID | Parent ID | Ticket subject | Description (VN/JP) | Ticket Type | Source ID | Version/Release | Activity | Progress (%) | Status | LOC | Test Case | Start date (mm/dd/YYYY) | End date (mm/dd/YYYY) | Estimate (H) | Actual (H) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Measurement tool | 4389 |  | [Document] Investigate GA report |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-03 | 2015-12-22 | 8.5 | 0 | 1: 8.5
| Measurement tool | 4390 |  | 「TEST」テストケースを準備してください |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2015-12-04 | 2015-12-04 | 8 | 0 | 1: 30.5
| Measurement tool | 4391 |  | [Testing] Execute test before/after release |  | Test | Cowell Redmine |  | Test |  | Closed | 0 |  | 2016-12-05 | 2016-12-23 | 93.5 | 0 | 1: 93.5